## OA Event Budget Form
OA Event Budget Planner and Control Sheet
Lodge/Chapter: |  |  |  | 60-Day Benchmark Date: | -60
Event Title: |  |  |  | 60-Day Bencmark Attend: | 0
Event Start Date: |  |  |  | 30-Day Benchmark Date: | -30
Event Location: |  |  |  | 30-Day Bencmark Attend: | 0
Lodge Advisor: |  |  |  | 14-Day Benchmark Attend: | 0
Lead Volunteer: |  |  |  | On-line Registration: | Yes |  | No
Cost Center: |  |  |  | On-line Payments: | Yes |  | No
ESTIMATED REVENUE |  |  | BUDGET | ACTUAL REVENUE |  |  |  | ACTUAL
Participant Type | Est. # Participants | Fee |  | Participant Type | Actual # Participants | Fee
Ordeal Candidate |  | 0 | 0 | Ordeal Candidate |  | 0 |  | 0
Brotherhood Candidate |  | 0 | 0 | Brotherhood Candidate |  | 0 |  | 0
Vigil Candidate |  | 0 | 0 | Vigil Candidate |  | 0 |  | 0
General Attendance (Current Members) |  | 0 | 0 | General Attendance |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
Total Participant Fees | 0 |  | 0 | Total Actual Participants | 0 |  |  | 0
Other Income (enter description below) |  |  |  | Other Income (enter description below)
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
Total Other Income |  |  | 0 |  |  |  |  | 0
TOTAL ESTIMATED REVENUE |  |  | 0 | TOTAL ACTUAL REVENUE |  |  |  | 0
ESTIMATED EXPENSES |  |  |  | ACTUAL EXPENSES
Program Supplies |  |  | 0 |  |  |  |  | 0
Food & Commissary Supplies |  |  | 0 |  |  |  |  | 0
Sanitation & Janitorial Supplies |  |  | 0 |  |  |  |  | 0
Facility Rental Fee (including council camp rentals req for non-service events) |  |  | 0 |  |  |  |  | 0
Recognition (Patches) |  |  | 0 |  |  |  |  | 0
Equipment Rental |  |  | 0 |  |  |  |  | 0
Printing/Postage |  |  | 0 |  |  |  |  | 0
Ordeal Recog. ($20 per person) |  |  | 0 | Ordeal Recog. ($20 per person) |  |  |  | 0
Brotherhood Recog ($15 per person) |  |  | 0 | Brotherhood Recog ($15 per person) |  |  |  | 0
Other Recognition |  |  | 0 |  |  |  |  | 0
Other Costs |  |  | 0 |  |  |  |  | 0
Expense Contingency (10% of expenses) |  |  | 0 |  |  |  |  | 0
Administration Fee (10% of total estimated revenue) |  |  | 0 | Administration Fee (10% of total estimated revenue) |  |  |  | 0
TOTAL ESTIMATED EXPENSES |  |  | 0 | TOTAL ACTUAL EXPENSES |  |  |  | 0
NET Difference + OR (-) |  |  | 0 | ACTUAL NET Difference + OR (-) |  |  |  | 0
Approvals |  |  |  | Close-Out
Lead Volunteer:_____________________________ |  | Date: | _____________ | Lead Volunteer:________________________ |  | Date: |  | _________
Staff Advisor:_______________________________ |  | Date: | _____________ | Staff Advisor:__________________________ |  | Date: |  | _________
Staff Leader:________________________________ |  | Date: | _____________ | Staff Leader:__________________________ |  | Date: |  | _________
February 2021 Revision

## BACKDATER
OA Event Planning Backdater
Lodge/Chapter: | 0
Name of Event: | 0
Event Start Date | 0
Event Location | 0
Staff Adviser | 0
Lead Volunteer | 0
Cost Center | 0
Task | Days Before Event | Date Due | Person Responsible
Reserve LHC facilities (if needed) | -365 | -365
Recruit event chair | -270 | -270
Recruit event committee | -240 | -240
Recruit Short-Term Camp Administrator | -240 | -240
Complete event site appraisal (non-council sites) | -210 | -210
Develop event budget | -200 | -200
Develop event marketing and promotion plan | -200 | -200
Submit completed event approval packet to Lodge Adviser (see checklist) | -180 | -180
Event Committee Meeting - develop theme and program | -180 | -180
Event Committee Meeting | -150 | -150
Confirm location (LHC sites) or Secure location (non-council sites) and permits | -150 | -150
Set up and open event registration | -120 | -120
Set up Facebook/social media event | -120 | -120
Update website | -120 | -120
Event Committee Meeting | -120 | -120
Recruit medical officer | -120 | -120
Recruit needed event staff | -120 | -120
eNews/Roundtable Save the Date/Invite | -120 | -120
Event Committee Meeting | -90 | -90
Order recognition items (patches, prizes, etc.) | -90 | -90
Prepare/distribute event flyer | -90 | -90
eNews/Roundtable Invite | -90 | -90
Begin Facebook/social media promotion | -90 | -90
Event Committee Meeting. -60 Day Registration Benchmark | -60 | -60
Order portable toilets, water buffalos, etc. | -60 | -60
Arrange for religious observance | -60 | -60
Prepare menu (if offering food service) | -60 | -60
eNews/Roundtable Invite | -60 | -60
Complete/distribute event program guide | -60 | -60
Site walk through | -60 | -60
Complete event security plan | -60 | -60
Complete event emergency procedures | -60 | -60
Recruit ceremonies teams | -60 | -60
Boost Facebook/social media event | -45 | -45
Event Committee Meeting. -30 Day Registration Benchmark | -30 | -30
Confirm Short-Term Camp NCAP requirements | -30 | -30
Early/Discount registration deadline | -30 | -30
Confirm event staff | -30 | -30
Prepare event signage | -30 | -30
Receive dietician menu approval (if offering food service) | -30 | -30
Notify local police, fire, EMS, hospital of event. Arrange traffic control and on-site communications. | -30 | -30
eNews/Roundtable Reminder | -30 | -30
Confirm ceremonies teams | -30 | -30
Contact Ranger/Caretaker about service projects | -30 | -30
Event Committee Meeting. -14 Day Registration Benchmark | -14 | -14
Final Site walk through/Complete Event Safety Checklist | -14 | -14
Finalize physical arrangements, activity locations, campsites, service projects) | -14 | -14
Reqest insurance certificates | -14 | -14
Request any needed printing | -14 | -14
Ceremonies team practice | -14 | -14
Recruit Elangomats | -14 | -14
Secure Ordeal/Brotherhood/Vigil recog. Items | -14 | -14
Pick up all needed materials | -7 | -7
Pick up/order food (if offering food service) | -7 | -7
Ceremonies team paractice/on-site preparation | -7 | -7
Prep service projects | -7 | -7
Submit final printing requests (schedules, etc) | -7 | -7
Send event update/reminder email to registrants | -3 | -3
Physical set up of events | -1 | -1
Event | 0 | 0
Complete Short-Term Camp Assessment | 0 | 0
Capture photo/video at event | 0 | 0
Day of event Facebook/social media post | 0 | 0
Submit any payments collected at event | 1 | 1899-12-31
After event satisfaction survey sent | 1 | 1899-12-31
Prepare and send Thank Yous | 2 | 1900-01-01
Submit Incident/Near Miss Reports | 3 | 1900-01-02
After event satisfaction survey reminder | 3 | 1900-01-02
After event wrap up meeting | 7 | 1900-01-06
Complete event close out (see checklist) | 30 | 1900-01-29
Formulas:
Date Due = B5+[Days Before Event]

## MARKETING PLAN
Event Marketing and Promotion Plan
Lodge/Chapter: | 0
Event Title: | 0
Event Date: | Begin: | 0 | End:
Event Time: | Begin: |  | End:
Event Location: | 0
Event Summary:
Event Contact Person | Name: |  | Phone: |  | Email:
Event Registration Link:
MESSAGE | DAYS OUT | DUE DATE | TARGET AUDIENCE | PERSON RESPONSIBLE | NOTES | PRIORITY
ONLINE
Registration/Website | -120 | -120 | Lodge/Chapter Members | Lodge Adviser |  | HIGHEST
Council E-News | -120 | -120 | Lodge/Chapter Members | Lodge Adviser/Event Chair | Save the Date
| -90 | -90 | Lodge/Chapter Members | Lodge Adviser/Event Chair | Invite/Save
| -60 | -60 | Lodge/Chapter Members | Lodge Adviser/Event Chair | Invite
| -30 | -30 | Lodge/Chapter Members | Lodge Adviser/Event Chair | Reminder
SOCIAL MEDIA
Facebook Event | -120 | -120 | Lodge/Chapter Members | Lodge Adviser/Event Chair
Facebook Promotion | -90 | -90 | Lodge/Chapter Members | Event Chair/Promo Lead
| -60 | -60 | Lodge/Chapter Members | Event Chair/Promo Lead
| -55 | -55 | Lodge/Chapter Members | Event Chair/Promo Lead
| -53 | -53 | Lodge/Chapter Members | Event Chair/Promo Lead
| -51 | -51 | Lodge/Chapter Members | Event Chair/Promo Lead
| -49 | -49 | Lodge/Chapter Members | Event Chair/Promo Lead
| -47 | -47 | Lodge/Chapter Members | Event Chair/Promo Lead
| -45 | -45 | Lodge/Chapter Members | Event Chair/Promo Lead
Boosted Event | -45 | -45 | Lodge/Chapter Members | Event Chair/Promo Lead | 2 week boost | If budget allows
| -38 | -38 | Lodge/Chapter Members | Event Chair/Promo Lead
| -31 | -31 | Lodge/Chapter Members | Event Chair/Promo Lead
| -24 | -24 | Lodge/Chapter Members | Event Chair/Promo Lead
| -17 | -17 | Lodge/Chapter Members | Event Chair/Promo Lead
| -10 | -10 | Lodge/Chapter Members | Event Chair/Promo Lead
| -7 | -7 | Lodge/Chapter Members | Event Chair/Promo Lead
| -5 | -5 | Lodge/Chapter Members | Event Chair/Promo Lead
| -3 | -3 | Lodge/Chapter Members | Event Chair/Promo Lead
| -1 | -1 | Lodge/Chapter Members | Event Chair/Promo Lead
| 0 | 0 | Lodge/Chapter Members | Event Chair/Promo Lead | DOE Post
Lodgemaster Email Blast
Email | -90 | -90 | Lodge/Chapter Members | Event Chair/Promo Lead
Ordeal Candidate Reminder | -90 | -90 | Lodge/Chapter Members | Event Chair/Promo Lead
Brotherhood Candidate Reminder | -90 | -90 | Lodge/Chapter Members | Event Chair/Promo Lead
Registration Reminder | -60 | -60 | Lodge/Chapter Members | Event Chair/Promo Lead
Registration Reminder | -30 | -30 | Lodge/Chapter Members | Event Chair/Promo Lead
Ordeal Candidate Reminder | -30 | -30 | Lodge/Chapter Members | Event Chair/Promo Lead
Brotherhood Candidate Reminder | -30 | -30 | Lodge/Chapter Members | Event Chair/Promo Lead
Registration Reminder | -15 | -15 | Lodge/Chapter Members | Event Chair/Promo Lead |  | Prices go up 10 days out reminder
Final Reg. Reminder | -5 | -5 | Lodge/Chapter Members | Event Chair/Promo Lead |  | Inlcude registration close date
Pre-Event Info Email | -3 | -3 | Event Registrants | Event Chair/Promo Lead |  | Include all needed participant info
PRINT MEDIA
Flyers/Invite | -90 | -90 | Lodge/Chapter Members | Lodge Adviser/Event Chair |  | Final date of completion
Event Program Guide | -60 | -60 | Lodge/Chapter Members | Event Chair
Optional with approval
Save the Date | -180 | -180 | Lodge/Chapter Members | Lodge Adviser/Event Chair |  | If budget, time, & volunteers allow
Reminder Postcard | -45 | -45 | Lodge/Chapter Members | Lodge Adviser/Event Chair |  | If budget, time, & volunteers allow
Videos | -45 | -45 | Lodge/Chapter Members | Lodge Adviser/Event Chair |  | If budget, time, & volunteers allow
Formulas:
DUE DATE = (C4+[Begin:])

## Important Info
Use the information below to help you complete the Budget Planning form.
Cost Center | What's it for: | Meals (Average costs per meal per weekend)
|  |  | Cost | # | Total
1-2371-994-00 | Section & National Activities | Breakfast | 3 | 2 | 6
| Conclave | Lunch | 4.5 | 1 | 4.5
| NOAC | Dinner | 5.5 | 1 | 5.5
| Section and National Training - NLS/DYLC | Snack | 2 | 2 | 4
1-2371-995-00 | Chapter Events | Avg total per wknd per person: |  |  | 20
Chapter activation events
Typical Event Fees
1-2371-996-00 | Lodge Events
| Winterfest | Ordeal Candidate | 50
| Summer Social (Puma Games) | Brotherhood Candidate | 40
| Banquet | Vigil Candidate | 25
| Lodge Leadership Development (LLD) | Vigil Breakfast | 5
|  | Current Members | 25
1-2371-997-00 | Lodge Ceremonial & Service Weekends | Fees may be adjusted based on budget needs. Do not go below these costs.
| Ordeals | Adjust current member fees first, do not increase Ordeal fees.
Brotherhood Events
| Vigil Weekend | Recognition
1-2371-998-00 | Lodge Trading Post | Ordeal Packet = | $20 per person
| Patch purchases not tied to a specific event |  | Includes: Sash, book, flap
| Clothing and othe rlodge merchandise purchaces and sales. | Brotherhood = | $15 per person
Includes: Sash
Expense Contingency (10% of expenses) = unexpected cost buffer
Administrative Fee (10% of total estimated revenue) = Insurance, registration system costs, other event administrative and support costs